DOSSIER TECHNIQUE

Porte cockpit

Contenu du dossier

Lexique : Anglais – Français						DT 2

Service bulletin							DT 3      à  DT 9

Plans et figures							DT 10    à  DT 20

Procédure pose insert						DT 21

Fiche technique insert NAS 1835 et vis Torq-Set NAS 1102	DT 22

Tableau des couples de serrage					DT 23   et  DT 24

Exemple synoptique d’assemblage : détails D et E			DT 24

Tableau des temps technologiques					DT 25

Planning prévisionnel initial						DT 26

Données de coûts							DT 26

Lexique

| adhesive | Adhésif /résine/colle |
| --- | --- |
| armoured | blindé |
| bolt | boulon |
| bracket | support |
| cured | Séché |
| debur | ébavurer |
| discard | Jeter, supprimer |
| drill | percer |
| edge | Arrête / bord |
| elongation | Allongement/ovaliser |
| eye end | Chape |
| fasteners | fixations |
| filler | remplissage |
| flows out | déborder |
| foil (decor) | Feuille décor/plaquage |
| galley | Espace cuisine |
| hole | Trou |
| jamming | Interférer /coincer |
| latch | loquet |
| lavatory | toilettes |
| ledge | rebord |
| lift | soulever |
| lining panel | Revêtement habillage |
| lint free | Non pelucheux |
| lock | verrou |
| lock nut | Ecrou freiné |
| match | Correspond / ajuster |
| nut | écrou |
| pin | Broche / goupille |
| placard | étiquette |
| profile | profilé |
| request | demande |
| retained | conservé |
| screw | vis |
| sealant | mastic |
| sheet | Feuille |
| skin | Peau / revêtement |
| skirting | Plinthe / enjoliveur |
| spacer | entretoise |
| strip | bande |
| syringe | seringue |
| washer | rondelle |
| wrinkles | Plis /rides |

SB

Installation d’une porte de cabine de pilotage renforcée

ATA 52

1 RAISON/DESCRIPTION/CONSEQUENCES OPERATIONNELLES

 Il a été demandé la redéfinition urgente de la structure des portes de cockpit pour prévenir ou retarder l'accès forcé dans le cockpit par les occupants de la cabine.

Le renforcement de la structure de la porte du poste de pilotage a été déterminé comme la solution la plus efficace pour répondre aux demandes de l'exploitant à court terme. Ce bulletin de service (SB) énonce la procédure pour installer le renforcement de la porte du cockpit.
La réalisation de ce bulletin de service permettra d'éviter ou de retarder l'accès forcé dans le cockpit de la cabine.

TRAVAIL ADDITIONNEL A APPLIQUER AVEC CE SB

RAISON

Un exploitant a signalé, à l'altitude de croisière, que la porte de cockpit se coince à cause de la tolérance inadaptée des composants. Après que la porte avait été ouverte par l'équipage de conduite, il n'était pas possible de la refermer parce que les verrous n’étaient plus en ligne avec leurs logements.

Après ce travail additionnel aucun problème de coincement, blocage ou autre n’a été signalé.

Cette révision nécessite un travail supplémentaire qui comporte l'allongement des trois trous des trois dispositifs de verrouillage dans la pièce 58.

EVALUATION TABLE 

 COMPLIANCE                 Desirable            CANCELS INSPECTION SB       No 
 POTENTIAL AD               No                   A/C OPERATION AFFECTED      No 
 RELIABILITY AFFECTED       No                   PAX COMFORT AFFECTED        No 
 COST SAVING                No                   ETOPS AFFECTED              No 
 STRUCTURAL LIFE EXTN       No                   VENDOR SB INVOLVED          No 
 KIT PRICE (€)              See SB

A	MATERIEL

Composants à changer:

Profils, raccords, loquets, équerres, panneaux, étiquettes, revêtements de couverture, angles, caisson, faisceau, feuilles de décor et éléments de fixation connexes.

B.   EXIGENCES COMPLEMENTAIRES

Aucune 


C.  DESCRIPTION 

To accomplish this Service Bulletin it is necessary to :

(1)  Remove the cockpit door. 

     (2)  Install Kit D02 

           (a)  At the cockpit door remove the profiles, the lock, the 
                peephole, the mirror and the decor foil. 

           (b)  At the cockpit door install the sheets, the profiles, the 
                latches, the l-profiles and the decor foil and at the galley 
                and lavatory wall profiles. 

           (c)  Additional Work 

                1  Do the elongation of the three holes for the three lock 
                    latches, in the item 58. 
                2  Match the contour of the holes in the lavatory wall to the 
                    dimensions of the elongated holes in the profile, item 58. 

     (3) Install the cockpit door.

D.  COMPLIANCE 

     Classification :    Desirable 
     
          ADDITIONAL WORK 

The accomplishment of the additional work of this Service Bulletin is desirable.

E.   MANPOWER 

The manpower estimates given in this Service Bulletin are based on the direct labor cost to do the work.

Time in HOURS:

Get Access in the cockpit,       		                     0.25 h
Remove the door                                               ...1 h

Install kit D02                                             à définir

Install the door in the cockpit                               ...2 h

Test the door                                                 0.10 h
          Close-up                                                      0.25 h

2.  MATERIAL INFORMATION 

A    PRICE AND AVAILABILITY

Kit D02 
                    Cost           : 1700    EURO  ( kit available)

Manufacturers Empty Weight : +7,82 kg      (+17.24 lb)

B.  INDUSTRY SUPPORT INFORMATION :

None

C.   LIST OF COMPONENTS

Kit D02 composition

ITEM   NEW PART No.        QTY UM KEYWORD

26     D2528641221800        1 EA BOLT 
29     D2528641222000        1 EA WASHER 
32     NAS1726CSE-4          2 EA NUT 
40     NAS1102-5-10          6 EA SCREW 
41     D2528641200000        1 EA LATCH 
42     D2528641200200        1 EA LATCH 
43     D2528641200400        1 EA LATCH 
44     D2528641121200        1 EA SHEET 
45     D258-ENAW2014 T2      1 EA SHEET 
46     D259-ENAW2014 T2      1 EA SHEET 
48     81842027              1 SM FOIL    
50     D2528641222800        1 EA PLATE 
51     NAS1102-3-6           2 EA SCREW 
53     NAS1835-3            12 EA INSERT 
55     D2528641223000        3 EA PROFILE 
56     D2528641221600        1 EA SPACER 
58     D2528641222600        1 EA SECTION 
59     NAS1102-5-8           19 EA SCREW 
60     NSA936603CC0100       2 EA CAP 
61     D2528641220400        1 EA LEDGE 
62     NAS1149D0416K         2 EA WASHER 
72     DAN319B01-500         5 ME FILM 
73     70864258            2.5 ME SKIRTING  
74     DAN319B01-25          6 ME FILM 
75     DAN98S2A              5 ME STRIP 
76     DAN98S2B              5 ME STRIP 
87     NAS1102-5-12         10 EA SCREW 
88     NAS1102-5-14          2 EA SCREW 
89     NAS1096-3-8           2 EA SCREW 
91     D2527700040000        1 EA PLACARD 
92     D2527701940500        1 EA PLACARD 
93     DAN316-3016           2 EA SCREW 
94     SJ-5514WHITE          1 EA BUMPER 
96     NAS1102-5-16          1 EA SCREW 
97     D2527487026200        1 EA SPACER 
98     NAS1102-3-7          18 EA SCREW 
99     NAS1169C10L          18 EA WASHER 
100    NAS1102-6-12          4 EA SCREW 
101    NAS1102-4-8           4 EA SCREW

D.   LIST OF MATERIALS — OPERATOR SUPPLIED 

     Consumable Materials

DESCRIPTION                      REFERENCE TO CML         QTY PER A/C INST DISP 
                                 MAT. No. 
Adhesive                         08-001                   As required 
Adhesive                         08-004A                  As required 
Adhesive filler                  08-022                   As required 
Adhesive                         08-010                   As required 
Adhesive Tape                    08-073                   As required 
Sealant                          09-016                   As required 
Cleaning agent                   11-026                   As required 
Coating Yellow Aluminum          13-002                   As required 
Polyurethane Primer              16-001C                  As required 


2  ACCOMPLISHMENT INSTRUCTIONS 
 A.   GENERAL 

     (1)  Preparation

(a)  Make sure that the aircraft is electrically grounded

(b)  Put the access platforms in position. 
       (c)  Open the passenger/crew 
       (d)  Remove the lining panel

(e)  Open, safety and tag  circuit breaker : LIGHT-CABIN ENTRY

(2)  Standard Practices 

       (a)  Torque the standard threaded fasteners, refer to AMM 20-21-11 
       (b)  Apply Sealant (Mat No.09-016) if needed to the interfaces of the structure and the new parts 

B.   MODIFICATION 

(1)  Remove the cockpit door, refer to AMM 52-51-11

(2)  Kit D02

(a)  At the cockpit door remove the profiles, the lock, the peepholes, the mirror and the decor foil.

Refer to Figure 3 

          1  At the cockpit door, as shown in Detail B and F, remove :

screws                                 Item (1)     retain 
               profile                                Item (2)     retain 
               mirror                                 Item (4)     retain 
               frame                                  Item (5)     retain 
               screws                                 Item (84)    discard 
               screws                                 Item (85)    discard 
               brackets                               Item (86)    retain 
               armour plate                           Item (80)    retain 
               screws                                 Item (81)    discard 
               armour plate                           Item (82)    retain 
               lock mechanism                         Item (7)     discard 
               screws                                 Item (8)     discard 
               lock mechanism                         Item (9)     discard 
               foil                                   Item (11)    discard 
               screws                                 Item (12)    retain 
               profile                                Item (13)    retain 
               cover                                  Item (14)    discard 
               screws                                 Item (15)    discard 
               profile                                Item (16)    retain 
               profile                                Item (17)    discard 
               screws                                 Item (18)    discard 

         2  At the cockpit door, as shown in Detail C, remove :

pivot pin                              Item (26)    discard 
               screws                                 Item (27)    discard 
               washers                                Item (28)    discard 
               pivot fitting                          Item (29)    discard 
               eye-end                                Item (30)    retain 
               lock nut                               Item (31)    retain 
               nut                                    Item (32)    discard 
               cover                                  Item (33)    retain

3  At the cockpit door, as shown in Detail D and E, remove :

screw                                  Item (21)    discard 
                washer                                 Item (22)    retain 
                spacer                                 Item (79)    discard 
            1   peephole                               Item (23)    retain 
            1   spacer                                 Item (24)    retain 
            1   peephole                               Item (25)    retain 
            1   peephole                               Item (23)    discard 
            1   spacer                                 Item (24)    discard 
            1   peephole                               Item (25)    discard 

        4  At the cockpit door remove the adhesive and clean the cockpit door with cleaning agent (Mat No. 11-026) .

(b)  At the cockpit door install: the sheets, the profiles, the latches, the l-profiles and the decor foil and at the galley and lavatory wall the profiles.

Refer to Figure 4 

        1  At the cockpit door, as shown in Detail J, K and L, install  : 
                12      inserts              NAS1835-3         Item 53 
        with adhesive (Mat No. 08-001)  and adhesive filler (Mat No. 08-022) . 
You have to transfert the position of the 12 previous holes on the inside door panel.

NOTE : Make sure that the holes in the sheet, Item 45, are in line with the marked holes in the cockpit door where you have to install the inserts.

2  At the cockpit door, as shown in Detail B, install :

1     block                                   Item 50 
                 2     screws               NAS1102-3-6        Item 51 
             and 
                 1     skirting                                Item 73   
             with adhesive (Mat No. 08-004A)


         3  At the cockpit door, as shown in Detail B, install : 

                 1     sheet                D258- 2014 T 2     Item 45 
                 1     sheet                D259- 2014 T 2     Item 46 
            with adhesive (Mat No.08-010) . 
            and 
                    armour plate                          Item (80) retained 
                    armour plate                          Item (82) retained 
            with 
                 1     foil                 -auto adhesive     Item 48  
                18     screws               NAS1102-3-7        Item 98 
                18     washers              NAS1169            Item 99 
                 6     screws               NAS1102-5-10       Item 40 
                10     screws               NAS1102-5-12       Item 87 
                 2     screws               NAS1102-5-14       Item 88 
                 1     latch                                   Item 41 
                 1     latch                                   Item 42 
                 1     latch                                   Item 43 


         4  At the cockpit door, as shown in Detail G and H, install :

3     l-profiles                             Item 55 
                 1     sheet                                  Item 44 
                 -     adhesive film                          Item 74 

          5  At the cockpit door bond these placards :

1   placard                                Item 91 
                 1   placard                                Item 92

6  At the cockpit door, as shown in Detail D, install : 

                 1   spacer                                  Item 97 
                 1   screw                NAS1102-5-16       Item 96 
             and 
                 1   washer                                Item (22) retained

7  At the cockpit door, as shown in Detail B, install : 

                     profile                                Item (2) retained 
                     profile                                Item (13)

profile                                Item (16) retained 
                8    screws         self tapping            Item (1) retained 
                8    screws         self tapping            Item (12) retained

8  At the cockpit door, as shown in Detail E, install :

mirror                                 Item (4) retained 
                     frame                                  Item (5) retained 
                  2  brackets                               Item (86) retained 
             with 
                  4  screws                NAS1102-6-12     Item 100 
                  4  screws                NAS1102-4-8      Item 101

9  At the cockpit door, as shown in Detail F, install : 

                  1  peephole                               Item (23) retained 
                  1  spacer                                 Item (24) retained 
                  1  peephole                               Item (25) retained

10 At the cockpit door, as shown in Detail C, install : 

                  1  pivot fitting                          Item 29 
                  2  nuts                 NAS1726CSE-4      Item 32 
                  1  spacer                                 Item 56 
                  1  pivot pin                              Item 26 
                  2  washers              NAS1149           Item 62 
                     eye-end                                Item (30) retained 
                     lock nut                               Item (31) retained 
                     cover                                  Item (33) retained

11 (ADDITIONAL WORK) Do the elongation of the three holes in the profile item 58 to the dimensions as shown in detail N.

At the lavatory wall, as shown in Detail N, install :

19     screws               NAS1102-5-8       Item 59 
                  2     screws                                 Item 93 
                  1     profile                                Item 58 
                  -     adhesive film                          Item 72

and drill three holes into the lavatory wall as shown in Section C-C.

Match the contour of the holes in the lavatory wall to the dimensions of the elongated holes in the profile, item 58, as shown in Detail N

12 At the lavatory wall, as shown in Detail N, install : 

                  1     bumper               SJ-5514 WHITE     Item 94

13 At the galley wall, as shown in Detail P, install : 

                  1     profile                               Item 61 
                  -     adhesive film                         Item 72

14 At the box assembly, as shown in Detail Q, remove : 

                  2  screws                              Item (89)  discard 
                  2  washers                             Item (90)  retain 
    and install : 
                  2  screws               NAS1096-3-8    Item 89 
                  2  washers                             Item (90)  retained

(3) Install the cockpit door, refer to AMM 52-51-11.

C.   TEST

(1)  Close and open the cockpit door to make sure that its moves smoothly. 
     (2)  Remove the safety clip and tag and close this circuit breaker. 
     (3)  Do the test after the removal/installation of the cockpit door,

D.   CLOSE UP

(1)  Make sure that the work areas are clean and clear of tools and other items of equipment. 
     (2) Close the passenger/crew door

(3) Remove the access platforms. 
     (4) Disconnect the aircraft electrical ground-connection

E.   DOCUMENTATION 

    Write in the applicable aircraft records that you have done all the work given in this Service Bulletin.

FIGURES

--------------------------------------------------------------------------------

Figure 3 Sheet 1

Modification of the armoured Cockpit Door (BEFORE)

Figure 3 Sheet 2

Modification of the armoured Cockpit Door (BEFORE)

Figure 3 Sheet 3

Modification of the armoured Cockpit Door (BEFORE)

Figure 4 Sheet 1

Modification of the armoured Cockpit Door (AFTER)

Figure 4 Sheet 2

Modification of the armoured Cockpit Door (AFTER)

Figure 4 Sheet 3

Modification of the armoured Cockpit Door (AFTER)

Figure 4 Sheet 4

Modification of the armoured Cockpit Door (AFTER)

Figure 4 Sheet 5

Modification of the armoured Cockpit Door (AFTER)

Figure 4 Sheet 6

Modification of the armoured Cockpit Door (AFTER)

Figure 4 Sheet 7

Modification of the armoured Cockpit Door (AFTER)

Figure 5 Sheet 1

Elongation of the Holes for the Lock Latches

Installation of Insert Nut Attachment

WARNING: 	PUT ON PROTECTIVE CLOTHING - DO NOT SMOKE./DO NOT BREATHE THE GAS.

- Drill the insert hole

- Transfert the position of the holes on the panel

- Carefully drill a hole in the upper skin of the door:

+ 4 mm wider than the insert radius

+ 3 mm deeper than the insert length

- Preparation for Installation

(a) Carefully remove the damaged honeycomb.

(b) Debur the edges with an emery cloth, grade 120.

(c) Clean area with cleaning agent (Mat No. 11-010) and a lint-free cotton cloth

(d) Fill the prepared area with bonding and adhesive (Mat No. 08-022).

Panel must be in horizontal position to prevent resin flow.

(e) When the adhesive is cured (2h at 20°c), use an emery cloth, grade 120 to make repair area smooth.

(f) Drill a hole into the filler:

+ 0.5 mm longer than the length of the insert.

+ 0.5 mm wider than the flange diameter of the insert you want to install.

(g) Clean the area: CLEANING AGENT (MatNo.11-010) and a lint-free cotton cloth

- Install the insert.

(a) Install the insert and hold it in position with the positioning washer

(b) Use a syringe and fill the area around the insert through the injection hole with bonding and adhesive compound (Material No. 08-001) until the adhesive flows out of the overflow hole.

(c) When the adhesive is cured, remove the positioning washer.

(d) Clean the area: cleaning agent (MatNo.11-010) with a lint-free cotton cloth.

Tableaux des couples de serrage

Code diamètre partie filetée (première colonne)

Ex:   NAS   1131  –  3     –  12

Code longueur

(suite sur le DT24)

ALL

Synoptique d’assemblage : détails D , E et F   figure 4 feuille 3

Assemblage détail D						Assemblage détail E

PORTE

86

100

4

5

101

PORTE

25

23

24

PORTE

97

22

96

Assemblage détail  F

Tableau des temps technologiques

Temps unitaires (Tu)  en dixièmes d’heures (dh)        exemple:  1 heure =10 dh      1 dh= 6 minutes

Exemple : pose de 3 vis serrées à la clef dynamométrique : Qté=3 donc  0.50 x 3 - Tu=1.5 dh

| Qté | Tu en dh |
| --- | --- |

Installer des pièces ou des composants à la main

| Empilement ou maintien de 1 à 3 pièces ensemble | 0.20 x Nbre |  |  |
| --- | --- | --- | --- |
| Empilement ou maintien de 4 à 6 pièces ensemble | 0.40 x Nbre |  |  |

Assemblage par vis – avec ou sans rondelle – inclus le serrage

| Serrage, « torquage » angulaire à la main | 0.20 x Nbre |  |  |
| --- | --- | --- | --- |
| Serrage, « torquage » à la clef dynamométrique | 0.50 x Nbre |  |  |
| Serrage, « torquage » à la clef dynamo+frein filet | 0.80 x Nbre |  |  |

Assemblage écrou – avec ou sans rondelle – inclus le serrage

| Serrage, « torquage » angulaire à la main | 0.20 x Nbre |  |  |
| --- | --- | --- | --- |
| Serrage, « torquage » à la clef dynamométrique | 0.50 x Nbre |  |  |

Pose de mastic ou d’adhésif  ou de résine de remplissage

| En cartouche par cordon | 1.00 x ml |  |  |
| --- | --- | --- | --- |
| Sur grande surface au rouleau | 0.50 x m2 |  |  |
| Localement pour densifier un logement d’insert | 0.30 x Nbre |  |  |

Pose de film de colle ou d'autoadhésif et marouflage

| Zone locale < 100 cm2 | 0.20 x Nbre |  |  |
| --- | --- | --- | --- |
| Zone étendue > 1 m2 | 0.50 x m2 |  |  |

Mise en position d’un insert

| Pose « humide » sans injection | 0.20 x Nbre |  |  |
| --- | --- | --- | --- |
| Pose et injection de résine avec une seringue | 0.50 x Nbre |  |  |

Perçage /fraisage – diam 3 à 18 mm

| Avec canon de perçage via un outillage | 0.50 x Nbre |  |  |
| --- | --- | --- | --- |
| En l’air, guidé ou non par un tripode de perçage | 0.30 x Nbre |  |  |
| Ovalisation à la fraise , travail de retouche | 0.40 x Nbre |  |  |

Traçage et report d’une position de perçage sur panneau

| Avec prise de mesures | 0.50 x Nbre |  |  |
| --- | --- | --- | --- |
| Avec utilisation d’un gabarit ou d’un calque | 0.10 x Nbre |  |  |

Trépanage de peau de faible épaisseur à la scie cloche

| Diamètre 12 à 20 | 0.20 x Nbre |  |  |
| --- | --- | --- | --- |
| Diamètre 21 à 40 | 0.40 x Nbre |  |  |

Pointage  – diam 2 à 6 mm

| Sur matériaux composites | 0.25 x Nbre |  |  |
| --- | --- | --- | --- |
| Sur alliages d’aluminium | 0.20 x Nbre |  |  |

Enlever résidus nid d’abeille- profondeur < 25 mm

| Diamètre 12 à 24 mm | 0.20 x Nbre |  |  |
| --- | --- | --- | --- |
| Diamètre 25 à 40 mm | 0.30 x Nbre |  |  |

Ebavurage manuel

| Avec outil coupant | 0.10 x Nbre |  |  |
| --- | --- | --- | --- |
| Au papier à poncer "émeri" | 0.20 x Nbre |  |  |

Nettoyage avec tissu coton- avec ou sans solvant

| Zone locale < 100 cm2 | 0.20 x Nbre |  |  |
| --- | --- | --- | --- |
| Zone étendue > 1 m2 | 1.00 x m2 |  |  |

Ponçage léger

| Zone locale < 5 cm2 | 0.05 x Nbre |  |  |
| --- | --- | --- | --- |
| Zone étendue > 1 m2 | 1.00 x m2 |  |  |

Début du planning prévisionnel initial (A) en suivant l’ordre de la gamme donnée dans le SB :

Le délai escompté par la compagnie pour effectuer ce SB sur toute sa flotte, 20 aéronefs strictement identiques, est de 21 jours.

L'aéronef vole quotidiennement en vols intérieurs   7j/7 de 7h à 22h et rejoint sa base tous les soirs.

Le travail est réalisé par : 		- un opérateur spécialisé qui  travaille de 23h à 6h

- un opérateur spécialisé qui  travaille de 6h à 13h

Début du travail à 23h après nettoyage de la cabine - Reprise des vols chaque jour à 7h

| Zones / / heures | 23 | 0 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | Immobilisation Heures de Vol |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
| Aéronef en hangar | ACCE | DEPO |  |  |  |  |  |  |  |  |  | REPO |  |  | …. h |
| Atelier composites |  |  | INST |  |  | INST |  |  |  |  |  |  |  |  |  |
| Etuve de séchage |  |  |  | CURE | CURE |  |  |  |  |  |  |  |  |  |  |
| Atelier assemblage |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

Conseil : mettre un code « couleur ou hachure »  pour chaque tâche

Nota : On prendra pour cette partie de l’étude les temps arbitraires suivants (pauses incluses et heures arrondies)

ACCE : accès aéronef et préparation de la zone de travail		1h		ASBL: assemblage kit sur porte  (phases 15 à 100)			         2h

DEPO : dépose porte de l’appareil 					1h		EXIT : rangement, test et remise en service aéronef		         1h

REPO : repose porte d’origine aéronef après installation kit 	2h		PNVE: repose d'une porte renforcée en échange de la porte déposée   2h

ADDW: travail additionnel	(phases 110 à 140)			1h		INST : travaux réalisés au poste de pose insert atelier composites         2h

CURE: séchage adhésif de remplissage cavité en étuve		2h		COLL: séchage adhésif de collage insert en étuve			          2h

La compagnie émet la possibilité d’acheter une seule porte neuve renforcée et prête à être installée.

Une porte neuve renforcée ou une porte déposée antérieurement et déjà équipé du kit lors de l’entrée de l’aéronef en hangar, sera considérée comme « neuve » et prête à poser (PNVE).

Nota : Le travail additionnel devra être fait « au plus tôt » dans la planification des tâches.

Données de coûts :

- Opérateur qualifié pour toutes les taches, travail en horaires décalés: 		       60 	€/h

- Immobilisation aéronef quand l'avion ne peut assurer les vols prévus : 		   5000 	€/h

- Achat porte de cockpit neuve , renforcée et prête à monter				12 000 	€

- Kit  D02 de modification porte originelle (visserie incluse)				  1 700		€